#### Process Pathway Following the
Non-structural Options Workshop

This flow chart summarises continued development and eventual implementation of non-structural measures.

Project scope and establish working group

HRFMAC Meeting

13 March 2000

Non-structural Options Workshop 10 April Provides guidance before involving the public

## PUBLIC INVOLVEMENT

Newsletter / Public Meetings

Continue developing measures through the NSOWG, including recommended investigations

HRFMAC Meeting

25 May 2000

## Verbal Report on Public Involvement Outcomes

Newsletter / Public Meetings

Modify Measures

Modify based on public feedback, guidance from HRFMAC and NSOWG

Form Final Set of Draft Measures

NSOWG provides substantial input to final draft set of measures

HRFMAC Meeting

29 June 2000

## Confirm Preferred Measures

Confirming general principals that support outcomes for Non-structural measures

COMMENCE IMPLEMENTING

NON-STRUCTURAL OPTIONS in JULY 2001

Includes forming policy and provisions for plan changes / developing specific EM measures