Report 00.34

2 February 2000

File: T/8/1/1

[0034.kpg]

Report to the Passenger Transport Committee

By Kevin Grace, Transport Infrastructure Co-ordinator

Current Status of Passenger Transport Infrastructure Projects

1.	Purpose

To update the Committee on the status of various passenger transport infrastructure projects.

2.	Background

At the Passenger Transport Committee meeting on 27 November 1997 the Committee requested that regular updates of the status of passenger transport infrastructure projects be provided.

3.	Comment

3.1	Waterloo Carpark Development

The hearing for our resource consent application was held on the 15th December 1999 at the Hutt City Council Chamber.  On the 24th December 1999 we were advised that our application to build a 61 space carpark on the grassed road reserve area adjacent to the Ambulance Station had been successful.  Consent was granted subject to 5 conditions, mostly concerning landscaping:

(1)	the landscaping of all areas shall be subject to the approval of the Hutt City Council

(2)	landscaping shall be subject to a continuing maintenance agreement also to be approved by Hutt City Council

(3)	trees are to be the largest size practical

(4)	Wellington Regional Council to liaise with the Ambulance Station re security concerns and possible traffic conflict with Ambulances

(5)	surface of the carpark to be rough and not conducive to skateboarding

Tender documents are being prepared and will be ready to go out within the next two weeks.  It is intended to have the carpark built by June of this year.

3.2	Paekakariki At Grade Crossing

Unfortunately no further information has been available from Tranz Rail.  We are still expecting the crossing to go ahead but do not know when.

4.	Communications

The Hutt News carried an article on our proposals early December, and a notice early January that consent had been granted.

5.	Recommendation

That this report be received for information.

Report prepared by:					Approved for submission by:

KEVIN GRACE	TONY BRENNAND

# Transport Infrastructure Co-ordinator	Manager, Transport Policy

DAVE WATSON

Divisional Manager, Transport